# Semester Project: Smart Parking Platform

Aliyan Adnan

University of Houston

Course Number: CIS 4374

Instructor Otto Dobretsberger

10/01/2026

Existing Software

Instead of focusing just on international examples, I concentrated on apps that individuals in Texas interact on a day-to-day basis. Drivers in Houston can utilize ParkHouston/ParkMobile, SpotHero, or ParkWhiz. Austin also offers Park ATX, which provides municipal parking. These applications demonstrate that users expect to pay, extend time, and book parking on their phones. The issue is that drivers may still be unsure whether a spot is available or whether they must pay to park, which entry to use, or what the approximate price will be, as some are also using prepaid features. The most crucial aspect of this project, in my opinion, is providing drivers with clear and real-time information.

- ParkHouston / ParkMobile (Houston)

- Advantages:

They provide a service through which one can pay for on-street and off-street parking by phone by entering a zone number, extending a session remotely, receiving expiration alerts, and reserving parking in some locations. It is already linked to City of Houston parking and is recognizable to those who park downtown.

- Disadvantages:

It is mostly designed around zone payments; the driver still has to know the proper zone and may not get a clear live image of all garage spaces, which can be confusing.

- Opportunities for improvement:

Showing a single map that incorporates street, lot, and garage space options, with clear availability status and access directions.

- SpotHero

- Advantages:

It can search the city’s locations, compare prices, reserve ahead of time, manage reservations, and book parking near airports, stadiums, and other attractions. Useful for events and travel since it allows drivers to assess choices before departing and save a lot of time.

- Disadvantages:

It primarily focuses on reservation marketplace; thus it does not focus on city meter payments or live empty space information.

- Opportunities for improvement:

Add verified live occupancy and make the app explain whether a space is reserved, when it will be available, or currently open.

- ParkWhiz

- Advantages:

It can search by city’s address, place, or event; compare location and price; reserve and prepay; use a mobile parking pass. It is very easy and simple layout for the bookings.

- Disadvantages:

It mainly focuses more on booking garages and lots rather than on managing city street parking or operator issues in real time, as it does not provide much useful data.

- Opportunities for improvement:

It can be vastly improved by connecting booking to operator updates, closures, and alternate options if the desired spot is occupied or unavailable.

- Park ATX

- Advantages:

It allows you to pay for eligible city parking, start or stop a session, extend time, receive expiration alerts, and view receipts and parking history. It uses a commonly used simple payment method that also supports pay by phone.

- Disadvantages:

This is exclusively designed for Austin city parking sessions rather than for a full multi-city reservation and operator platform, so it limits its own market.

- Opportunity for improvement:

This can be expanded a lot by building a platform that can support Texas cities while still letting each city keep its own rules, zones, rates, and notices so the drivers don’t have to rely on other services.

## What Makes My application Unique

There is nothing more frustrating than reserving a parking spot only to pull up to the garage and find that floor blocked off and you miss an event or get late for your meeting. This platform fixes disconnect by keeping drivers and operators on the same page. Drivers can see right away whether an open space is physically verified, an estimate based on recent trends, or still unconfirmed. Total pricing and cancellation rules are laid out clearly before checkout, so there are no surprises at the gate. And if something does go wrong at the facility, the app doesn't leave people stranded immediately points them to an open nearby garage or processes a quick refund on the spot.

### Vision and Scope

Project Vision:

Everyone knows the quiet panic of watching the time go by while circling the same packed parking lot in hope of finding space. Whether you are running late for an exam, rushing toward an airport terminal, or trying to catch a football match, the last thing you depend on is that parking spot that you can't seem to find, and it is now a guessing game. This platform cuts through that mess by keeping drivers and lot operators entirely in sync. Drivers can quickly pinpoint verified spots, pay clear upfront rates, and pull straight into an open space with confidence. Behind the scenes, garage managers get clean, practical insights to open or close levels, update pricing for busy hours, and track their occupancy without the usual operational headaches. Instead of drivers gambling in empty spaces and managers flying blind, it turns parking into an easy, reliable part of the day.

The Deliverable

Drivers get an option to track down spots, clear directions to their preferred map, and filter by essentials like EV chargers, vehicle height clearance, and accessible parking, while also showing whether a space is sensor-verified or time-estimated. On the other side, operators receive a clean dashboard that allows them to adjust surge rates, review occupancy, and shut down blocked ramps the second an accident or an issue arises.

Ground Realities

Development runs on a strict single-semester clock, requiring disciplined trade-offs and heavy reliance on proven third-party APIs for card transactions, merchants, mapping tiles, and access-control systems. Because spot projections are only as dependable as the garage's own incoming feeds, every release must carefully account for data gaps while meeting strict payment security, accessibility, and local consumer refund rules before launch.

Company and Project Overview

Company Background

WE ARE $oftware ¢orp. It is a student company formed to design and launch the Smart Parking Platform, as we were routinely penalized for showing up late to our 8:00 AM class not because we overslept, but because the campus parking structure was a daily nightmare. After missing a midterm while trapped in a stagnant line outside a garage that was secretly at capacity, our group spent a long weekend doing our research on the parking companies. That scrappy prototype eventually evolved into WE ARE $oftware ¢orp, a full-spectrum student development studio committed to killing urban gridlock through smart software. For this coursework scenario, we operate with zero financial or staffing limitations, focusing our energy on integrating external APIs smoothly.

How We Got the Job

We shaped our project around a public-private challenge: our city's transit authority needed a way to coordinate both municipal garages and commercial decks under a unified system. Rather than having drivers download three different tools and lot supervisors use four separate dashboards, our team stepped in to build a single system that connects drivers, garage staff, and municipal oversight.

The Core Concept

The project is straightforward, as it solves a real-life problem with no more guessing games at the barrier gate. Drivers choose their destination, lock in a verified spot, pay the exact fee upfront, and pull directly to the designated lane without circling. On the other side of the screen, lot owners get quick analytics view to adjust hourly fees, block off flooded ramps, and see real occupancy without checking stalls by hand, making the process smooth.

Software Requirements Specification (SRS)

System Overview & Operational Context

This draft SRS defines the initial functional and quality expectations for the Smart Parking Platform. The product is a cloud-hosted system with mobile and responsive web clients, an operator dashboard, an administrative console, and APIs that connect mapping, payment, notification, sensor, and facility access services.

| User Role | Primary Function & System Needs |
| --- | --- |
| Driver | finds parking spaces, completes pre-arrival transactions, accesses entry gates, and manages digital receipts. |
| Parking operator | Responsible for operational capacity, overrides bay allocations, tracks traffic, and manages lane shutdowns. |
| Finance user | Manages merchant payouts, monitors processing fees, reviews payment reversals. |
| System administrator | Control’s role permissions, manages API keys, sets monitoring alerts, and audits system access logs. |
| City transportation analyst | Reviews recurring parking trends, duration metrics, and peak curbside pressure points for transit optimization. |
| Merchants | Provides payments, maps, notifications, availability, or access-control events. |

- Functional Requirements: The specific features and actions the system must support. These define what users can do (search, reserve, pay, navigate, cancel) and what administrative or automated systems handle (lock spots, dispatch alerts, sync rates, handle gate failures).

- Non-Functional Requirements: The system's quality standards and constraints. Rather than features, these specify operational criteria such as surge time, speed/latency, data encryption, privacy, accessibility compliance, and traffic scaling.

- External System Integrations: The outside third-party services and hardware the platform relies on to function, such as mapping services, credit card gateways, barrier gate equipment, and push notification networks.

Use Cases

Driver Discovery & Booking

- Set Up Car & Profile

Actor: Driver

Flow: Driver saves vehicle height and license plate info once; system pre-configures automatic gate detection and vehicle clearance warnings for future trips.

Fallback: Plate conflict alerts driver to confirm registration before booking.

- Search for Parking

Actor: Driver

Flow: Driver inputs destination and arrival window; platform maps nearby garages, clearly tagging each lot as sensor-verified, trend-estimated, or offline.

Fallback: If zero spots match, system expands the search radius by 0.5 miles.

- Need-Specific Filtering

Actor: Driver

Flow: Driver filters for rapid EV charging, ADA access, or covered decks; map updates instantly to show only matching stalls.

Fallback: If no exact match exists, the system surfaces the closest partial alternative with clearly missing tags highlighted.

- Reservation Hold

Actor: Driver

Flow: Driver picks an open spot; system places a strict 5-minute database lock on that stall while displaying upfront costs and cancellation terms.

Fallback: If the checkout timer expires, the spot quietly returns to the open public pool.

- Pay for Parking

Actor: Driver, Payment Gateway

Flow: Driver approves itemized costs via Apple Pay, Google Pay, or saved card; gateway confirms payment and drops a digital receipt into the driver’s profile.

Fallback: Card decline alerts the driver immediately without dropping their 5-minute stall hold.

Arrival & Gate Entry

- Route to the Entrance

Actor: Driver, Navigation API

Flow: App transfers exact garage driveway coordinates not building into Apple or Google Maps for zero-confusion arrival.

Fallback: Road closures trigger an alternative alleyway or side-street entrance pin.

- Scan in at the Gate

Actor: Driver, Gate Controller

Flow: Garage camera reads the driver's license plate on approach and lifts the barrier automatically.

Fallback: If camera fails or plate is obscured, driver scans an offline-ready in-app QR code at the pedestal scanner.

- Get Gate Help

Actor: Driver, Support Agent

Flow: Barrier refuses to lift; driver taps "Help" in-app to generate a dynamic 4-digit keypad pin or trigger a remote buzzer override from the operator.

Fallback: Complete gate outage prompts the driver to proceed to an overflow lane with manual attendant check-in.

Session Management & Exceptions

- Add More Time

Actor: Driver

Flow: Driver receives a 15-minute expiration alert, taps "Extend 1 Hour," and the system charges the difference while extending gate privileges.

Fallback: If the facility is fully reserved for an upcoming event, the app warns the driver to vacate to avoid overstay fees.

- Cancel for a Refund

Actor: Driver, Payment Gateway

Flow: Driver cancels booking prior to the garage grace period; system unlocks the space for resale and queues an instant, full refund.

Fallback: Late cancellations calculate and display a partial cancellation fee before the user confirms.

- Emergency Rerouting on Deck Closure

Actor: Driver, Platform Engine

Flow: An operator closes a flooded deck containing booked spaces; app pings approaching drivers with a one-tap reroute to an adjacent affiliated lot at no extra charge.

Fallback: If nearby garages are full, platform issues an immediate full refund plus courtesy travel credit.

- Pay Late Fees

Actor: Driver, Payment Gateway

Flow: Driver exits 45 minutes past booking window; exit gate captures departure timestamp and automatically bills the prorated overstay fee to the saved card.

Fallback: Expired payment card prompts an in-app payment request before digital receipt generation.

Operator Control & Telemetry

- Track Open Spots

Actor: Sensor Network / Garage Gate

Flow: Ground loops and stall cameras transmit vehicle entries and exits; backend updates available stall counts within 60 seconds.

Fallback: If sensor pings stop for more than 5 minutes, the app automatically flags the garage inventory as "Estimated / Stale."

- Change Prices

Actor: Parking Operator

Flow: Operator raises event rates or lowers slow-day pricing from a simple browser dashboard; updated fees reflect instantly on the public map.

Fallback: Existing active reservations retain their locked-in booking price.

- Block Off Rows or Floors

Actor: Parking Operator

Flow: Operator toggles "Maintenance Mode" on Floor 3; platform instantly freezes bookings for those specific stalls while keeping other levels active.

Fallback: System flags any driver currently end route to that deck for reassignment.

Auditing & Analytics

- Download Daily Reports

Actor: Parking Operator, City Analyst

Flow: Manager selects a date range and exports clean CSV/PDF reports covering fill rates, peak arrival hours, and gross earnings; no technical help needed.

Fallback: Huge annual queries run asynchronously in the background and deliver a download link to email.

- End-of-Day Payments

Actor: Finance Specialist

Flow: System matches in-platform booking IDs against processor settlement payouts, automatically flagging unpaid dues or chargeback disputes.

Fallback: Mismatches generate an exception ticket with links to the corresponding transaction logs.

Work Breakdown Structure

To keep our development strategy grounded and practical, I based the Work Breakdown Structure (WBS) on how drivers and lot managers will engage with the platform daily, rather than a high-level list of features. The project spans the whole operational experience, from first user login and profile creation to real-time garage monitoring, payment processing, and administrative statistics. By moving every main element down at least three tiers, I've broken down the whole scope into bite-sized, manageable tasks. This level of specificity eliminates uncertainty, clarifies work items, and guarantees that each deliverable is modest enough for a single developer to manage and complete within our time.

Instead of a standard feature list, this Work Breakdown Structure organizes the Smart Parking Platform across four core operational areas. Each area is broken down into specific sub-tasks to ensure clear ownership and straightforward execution during development.

Driver-Facing Applications: Covers everything the driver interacts with, beginning with user onboarding, profile setup, and digital payment options. It controls lot discoveries using interactive maps and feature filters, reservation holds through upfront checkout, and active parking sessions such as time extensions or overstay charges.

Operator & Admin Portal: Concentrates on back-office controls for facilities managers. It has live telemetry dashboards for tracking real-time lot occupancy, dynamic price toggles for peak hours, maintenance overrides to block individual stalls or decks, and financial export capabilities for daily revenue audits.

Hardware & Gate Access Integrations: Connects software logic to actual garage hardware. This includes synchronizing License Plate Recognition (LPR) cameras for barrier entrance, installing offline QR scanners, enabling backup PIN access, and receiving live telemetry feeds from in-ground loop sensors and above stall cameras.

Engineering Management & Launch: This describes the technological underpinning and deployment processes. It includes early integration of core mapping and payment APIs, PCI-DSS compliance and security audits, comprehensive end-to-end integration testing, and the final cloud infrastructure deployment.

Project Timeline

| WBS ID | Task / Phase Name | Duration | Start Week | End Week | Dependencies |
| --- | --- | --- | --- | --- | --- |
| 1.0 | Requirements & Architecture Phase | 2 Weeks | W1 | W2 | X |
| 1.4.1 | System Architecture & Third-Party API Setup | 2 Weeks | W1 | W2 | None |
| 2.0 | Core Development Phase | 6 Weeks | W3 | W8 | X |
| 1.1.1 | Driver Setup, Profile & Payment Method Setup | 2 Weeks | W3 | W4 | 1.4.1 |
| 1.1.2 | Search, Map Filtering & Occupancy system | 3 Weeks | W4 | W6 | 1.1.1 |
| 1.1.3 | Reservation Hold & Payment Engine | 2 Weeks | W6 | W7 | 1.1.2 |
| 1.2.1 | Operator Telemetry & Rate Controls | 3 Weeks | W5 | W7 | 1.4.1 |
| 1.3.1 | Gate Access Integration (LPR, QR, PIN) | 3 Weeks | W6 | W8 | 1.1.3, 1.2.1 |
| 3.0 | Advanced Features & Edge Cases | 3 Weeks | W8 | W10 | X |
| 1.1.4 | Extensions, Overstays & Rerouting | 2 Weeks | W8 | W9 | 1.1.3 |
| 1.2.2 | Analytics, Reports & Payout system | 2 Weeks | W9 | W10 | 1.2.1 |
| 4.0 | Testing, Compliance & Rollout | 4 Weeks | W11 | W14 | X |
| 1.4.2 | System Security, PCI Audits & Testing | 2 Weeks | W11 | W12 | 1.3.1, 1.1.4 |
| 1.4.2.2 | Launch & Final Presentation | 2 Weeks | W13 | W14 | 1.4.2 |

GANTT CHART

Agile Task Management & Product Backlog (Trello)

https://trello.com/invite/b/6ab5a5f48c0beec860958379/ATTIb5c08fc72042298c91128aa436c4254eBD8C9930/smart-parking-platform

Implementation Strategy & Architecture

To connect high-level system design to everyday engineering execution, the Smart Parking Platform's Work Breakdown Structure (WBS) was converted into an organized Agile Scrum backlog using Trello. The platform's functional scope is divided into four key operating streams: authentication, user interfaces, core microservices, and analytical reporting. This is supported by an active Sprint 1 Backlog, which is aimed to deliver our first architectural baseline.

Each card includes thorough user stories, system dependencies, and technical details in order to uphold stringent project control and go beyond baseline criteria. In order to cover edge scenarios, hardware integration failovers, and compliance standards required for a production-grade platform launch, the backlog purposefully grows above baseline item needs.

Backlog Verification & Category Breakdown

- Category A: Login & Authentication (7): Establishes identity management, biometric authentication, role-based access control, and automated session timeouts.

- Category B: Operator & User UI (17): Encompasses responsive interfaces for driver discovery, live sensor status indicators, interactive level selectors, and operator override controls.

- Category C: Backend Processes (17): Houses core system engines, including dynamic pricing synchronization, automated stall reservation timers, LPR gate validation, and PCI-DSS payment tokenization.

- Category D: Reporting & Analytics (12): Delivers operational intelligence, including daily occupancy heatmaps, automated settlement logs, audit trails, and city-wide transit analytics.

- Sprint 1 Backlog (10): Prioritizes foundational deliverables for Weeks 1–2, focusing on cloud infrastructure setup, payment gateway integration, and primary authentication workflows.

Risk Management

Our team started this project because the campus garage was secretly full and we missed a midterm. Because of that, the risks I care about most are the ones that would give drivers wrong information again. In this section I list the risks for the Smart Parking Platform, score them in a Risk Register, and explain how our team will communicate. I connected each risk to our WBS tasks and use cases so they match the plan we already made.

Risks by Category

I found four risks for each category: technical, schedule, financial and people. Our scenario says we have no financial limits, so the financial risks are mostly about costs the platform would face after launch.

| Category | Risk | What could happen | Links to |
| --- | --- | --- | --- |
| Technical | Sensors or cameras stop sending data | A garage could show open spots when it is really full, which is the same problem that made us miss our midterm. | Use Case 13, WBS 1.2.1 |
| Technical | The plate reader (LPR) fails in heavy rain, glare or dark decks | The gate will not lift, so the driver has to use the QR code or PIN. | Use Cases 7 and 8, WBS 1.3.1 |
| Technical | Everyone tries to book at once before a big event | Football games and airport rushes could break the 5-minute spot hold and double book a stall. | Use Case 4, WBS 1.1.3 |
| Technical | Payment, map or notification services go down or change | Our plan depends on outside APIs, so drivers could not pay or get directions. | Ground Realities, WBS 1.4.1 |
| Schedule | Gate access work (1.3.1) starts late | It waits on 1.1.3 and 1.2.1, so any delay there moves it back. | WBS 1.3.1 |
| Schedule | Search, map filtering and occupancy (1.1.2) takes longer than 3 weeks | Reservations (1.1.3) cannot start until it is done. | WBS 1.1.2 |
| Schedule | The PCI-DSS audit finds problems | Fixing them could eat into the launch weeks (13-14). | WBS 1.4.2 |
| Schedule | The Trello backlog keeps growing | It already has more than 50 cards, and we only have one semester. | Trello Categories A-D |
| Financial | Card fees and chargebacks are higher than expected | Operators would get less money in their payouts. | Use Case 17, WBS 1.2.2 |
| Financial | Sensors, cameras and gate equipment cost too much | Hardware prices are hard to guess, and every garage needs it. | Hardware and Gate Access area |
| Financial | Event days bring huge traffic and a bigger cloud and map bill | Football matches and airport trips are the exact moments the app is used most. | Use Case 14, WBS 1.4.2.2 |
| Financial | Refunds and travel credits add up when a deck closes | A flooded Houston garage could mean many full refunds in one day. | Use Cases 10 and 11, WBS 1.1.4 |
| People | Teammates get busy with exams or 8:00 AM classes | Each WBS task is meant for one developer, so work could stop. | Whole timeline |
| People | Nobody on the team has used plate readers or payment APIs before | We would need extra time to learn them. | WBS 1.3.1 and 1.1.3 |
| People | It is unclear who owns what across the four WBS areas | Tasks could get missed or done twice. | All four WBS areas |
| People | Garage staff do not know how to use the operator dashboard | A flooded floor might stay open to drivers because nobody closed it. | Use Cases 14 and 15, WBS 1.2.1 |

Risk Register

This register has 16 risks. I scored each one by Probability as (P) times Impact  as (I), both from 1 to 5. A score of 15 or more is high, 8 to 14 is medium and under 8 is low. Status shows if the risk is still open, being watched, or accepted, and we will update it every week.

| ID | Risk | Category | P | I | Score | Response | What we will do | Owner | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R1 | Sensors or cameras stop sending data (Use Case 13) | Technical | 4 | 4 | 16 | Reduce | Mark the garage "Estimated / Stale" after 5 minutes with no data, and always show if a spot is sensor-verified or only an estimate | Hardware lead | Open |
| R2 | Plate reader fails in rain, glare or dark decks (Use Case 7) | Technical | 3 | 4 | 12 | Reduce | Test in low light; keep the QR code and 4-digit PIN backups (Use Case 8) | Hardware lead | Open |
| R3 | Everyone books at once before big events (Use Case 4) | Technical | 3 | 4 | 12 | Reduce | Lock the spot in the database for 5 minutes and load test with a fake event rush | Backend lead | Open |
| R4 | Payment, map or notification service goes down | Technical | 3 | 5 | 15 | Reduce | Test the APIs in Weeks 1-2 (WBS 1.4.1) and keep a backup payment option | Tech lead | Open |
| R5 | Gate access (1.3.1) starts late | Schedule | 4 | 4 | 16 | Reduce | Start hardware setup early and use a fake gate to test in the meantime | Project manager | Open |
| R6 | Search and map filtering (1.1.2) runs over 3 weeks | Schedule | 3 | 4 | 12 | Reduce | Build the basic map first and add EV, height and ADA filters after | Driver app lead | Open |
| R7 | PCI-DSS audit finds problems (1.4.2) | Schedule | 3 | 5 | 15 | Reduce | Use a payment gateway so we never store card numbers; do a practice check in Week 9 | QA lead | Open |
| R8 | Trello backlog keeps growing | Schedule | 4 | 3 | 12 | Avoid | Stop adding cards after Sprint 1; the project manager approves any new one | Project manager | Open |
| R9 | Card fees and chargebacks are too high (Use Case 17) | Financial | 3 | 3 | 9 | Accept | Show the full price before checkout and match payments to payouts every day | Finance lead | Monitoring |
| R10 | Hardware costs too much | Financial | 3 | 4 | 12 | Transfer | Get fixed quotes from vendors and start with one pilot garage | Project manager | Open |
| R11 | Event-day traffic raises cloud and map costs | Financial | 2 | 3 | 6 | Accept | Set usage alerts and a spending limit before the busy days | Tech lead | Accepted |
| R12 | Refunds and travel credits add up after a deck closes (Use Case 11) | Financial | 2 | 4 | 8 | Accept | Cap the travel credit and try rerouting to a nearby garage first | Finance lead | Accepted |
| R13 | Teammates busy with exams or 8:00 AM classes | People | 4 | 3 | 12 | Reduce | Have two people know each task and leave extra time in Weeks 13-14 | Project manager | Open |
| R14 | Team has not used plate readers or payment APIs | People | 3 | 3 | 9 | Reduce | Spend Weeks 1-2 on tutorials and sample projects and work in pairs | Tech lead | Open |
| R15 | Unclear who owns what in the four WBS areas | People | 3 | 3 | 9 | Avoid | Give every WBS item one owner and go over them in the weekly meeting | Project manager | Open |
| R16 | Garage staff cannot use the dashboard (Use Case 15) | People | 3 | 4 | 12 | Reduce | Make Maintenance Mode one tap, write a one-page guide and test it with a real operator | Operator portal lead | Open |

Red = high (15+), yellow = medium (8-14), green = low (under 8).

Communication Plan

Our team follows the same four areas as the WBS, so each area gets its own meeting schedule. Since we are students with classes and exams, I made the plan light: short daily updates in the group chat instead of long calls, and meetings set right after class days. In exam weeks we switch to chat updates only, except for the weekly status meeting.

| Team | Meeting | How often | Who joins | Why |
| --- | --- | --- | --- | --- |
| Whole project | Sprint planning and review | Every 2 weeks | Everyone and the instructor | Plan the next sprint, show what is finished, review the top risks |
| Project management | Status meeting | Once a week (30 min, after class) | Project manager and team leads | Check the timeline, update the Risk Register, fix blockers |
| Driver-Facing Applications | Daily update in group chat | Daily (5 min) | Driver app developers | Profile, search, reservation hold and payments: done, next, stuck |
| Operator & Admin Portal | Daily update in group chat | Daily (5 min) | Dashboard developers | Occupancy dashboard, price changes, floor closures and reports |
| Hardware & Gate Access | Check-in call | Twice a week (20 min) | Hardware lead and backend developers | Plate reader, QR, PIN and sensor progress and test results |
| Engineering Management & Launch | Security and testing review | Once a week | QA lead and tech lead | Testing, PCI checklist and launch readiness |
| Transit authority and garage operators | Feedback meeting | Every 2 weeks | Project manager and their reps | Show a demo and get feedback and approval |
| Exam weeks | Chat updates only | Daily | Everyone | Keep work moving without extra meetings |

Reporting Methods

I chose these methods so small problems are found early and big ones reach the project manager fast. Daily messages catch small blockers, the Trello board shows the real state of each task, and anything urgent goes straight to the project manager instead of waiting for the weekly meeting.

| Method | How often | Who gets it | Tool / format |
| --- | --- | --- | --- |
| Daily update | Daily | Own team | Short message in the group chat: done, next, stuck |
| Trello board | Always up to date | Whole team | Cards move from backlog to done |
| Weekly status report | Weekly | Project manager and instructor | One page: progress vs. timeline, top 3 risks, next steps |
| Risk Register update | Weekly | Team leads | Shared copy of the register with new scores and statuses |
| Sprint demo | Every 2 weeks | Transit authority and operators | Live demo with short slides |
| Urgent issue | Within 24 hours | Project manager | Direct message for any high risk or a delay of 2+ days |
| Meeting notes | After each meeting | Everyone | Notes saved in one shared folder |

References

- ParkHouston and ParkMobile Houston. https://park.parkmobile.io/tx/houston/parkhouston Accessed September 10, 2026.

- SpotHero Houston. https://spothero.com/city/houston-parking Accessed September 10, 2026.

- ParkWhiz Houston. https://www.parkwhiz.com/p/houston-parking/ Accessed September 10, 2026.

- Park ATX. https://play.google.com/store/apps/details?id=com.parkgenius.ParkGenius Accessed September 10, 2026